## Sheet1
Poornima College of Engineering Department of Information Technology Product Backlog (Project-II: 2018-19)
Epic | Sprint | User Story Role | User Story Name | Story Details | Tasks Items | Analyst / Prep work | Dev. Estimate | QA | Total User Story Hours
Careerheight$ | 1 | Jobseeker | Register personal details | A user needs to sign in for using the portal functionalities .The sign in will be done by user id and password | 1. Develop a registration page with mandatory fields (Name, Email address, Password, Mobile number, Job type) and optional fields . 2. The form will be submitted and entries will reflect in user table of DB. 3. Forgot password option will be available for a registered user where user can create a new password with a Verification question. 4. After successful registration, user will be required to be login through Login form with Uid and password. | 1 | 45 | 2 | 48
Careerheight$ | 2 | Jobseeker | Job search | The jobseeker can search for the jobs according to their requirements | 1. The users has the facility to see available services or vacancies 2. Can search for jobs 3. User will specify their area of jobs 4. Can apply for the jobs 5. User will upload their CV and required details. 6. Can update the profile details 7. Then form will be submitted and entries will reflect in user table of database 8. Available jobs are suggested to them according to the profile | 3 | 50 | 3 | 56
Careerheight$ | 3 | Employer | Manage accounts | Manage the system(upload the jobs) and accounts of jobseekers | 1. Login to the website 2. Can post the jobs 3 Delete jobs available according to requirement changes 4. Update the jobs 5. Approve the jobs for job seekers 6. Can view the details of registered applicants 7. Download the CV or application submitted by job seeker 8. Entries will reflect in the database | 3 | 40 | 2 | 45
Careerheight$ | 4 | Admin | Manage the system | Manage the system and accounts of jobseekers and Employer | 1. Admin can manage the accounts of applicants 2. Admin can manage the recruiters 3. Can manage the jobs 4. Can add the new jobs 5. Delete the available jobs as per requirement changes 6. Update or edit the jobs 7. Can view the details of the employee and job seekers 8. Can monitor every activity which is performed in the system 9. Download the CV or application submitted by job seekers. 10. Entries will reflect in Database | 3 | 60 | 2 | 65
Careerheight$ | 5 | Admin | Manage the system | Verification of required details | 1. Verification of details entered 2. Verification of documents 3. Generate CAPTCHA for the security purpose 4. Conduct standup meeting 5. Perform documentation work | 1 | 20 | 1 | 22
Careerheight$ | 6 | Admin | Conduct Interviews | Schedules the interviews of the shortlisted applicants | 1. Shortlist the applicants according to the company’s requirements and criteria 2. Schedule the interview dates 3. List out the selected candidates | 1 | 30 | 2 | 33
| Signature |  |  |  | Signature |  | Signature
| (Project Guide) |  |  |  | (Scrum Master) |  | (Project Coordinator)